## Sheet1
Product Backlog Spark Airways
Project ID: POD3 INTADM21AJ008
Done
User Story Id | User Story Name | User Story Role | User Story Details | Acceptance criteria | Priority | Sprint | Story Point | Done | Added in Sprint | Closed in sprint | Actual Story Points
USER_STORY_1 | Admin Login | Admin | Option for Admin Name and password will be provided and based on correct credentials, the Admin will be able to enter Admin portal. | Admin Name and password must match in the database table Admin | Critical | 1 | 5
USER_STORY_2 | Add Flight Schedule | Admin | The admin will be able to add Flight schedule in database by filling the Flight Schedule form. | Time be in the formal of "HH:MM:SS", Date must be in the formal of "YYYY-MM-DD", Seats and Costs must be integer value. The Admin must be Logged in before using this functionality. | Critical | 1 | 5
USER_STORY_3 | Show All Flight Schedules | Admin | The Admin must be able to see all flight Schedules and its whole data instead if flight schedule id. | The Admin must be Logged in before using this functionality. | Critical | 1 | 5
USER_STORY_4 | Delete Flight Schedule | Admin | The Admin have a right to delete Flight if any unfortunate condition happens. | The Admin must be Logged in before using this functionality. | Critical | 1 | 5
USER_STORY_5 | Update Flight Schedule | Admin | The Admin have a right to Update Flight if any changes happens in timing, source, destination etc. | The Admin must be Logged in before using this functionality. | Critical | 2 | 5
USER_STORY_6 | Add News Feed | Admin | The admin will be able to add News Feed in database by filling the Flight Schedule form. | Date must be in the formal of "YYYY-MM-DD", News must be of String Value.The Admin must be Logged in before using this functionality. | Critical | 2 | 5
USER_STORY_7 | Show All News Feed | Admin | The Admin must be able to see all News Feed and its whole data. | The Admin must be Logged in before using this functionality. | Critical | 2 | 5
USER_STORY_8 | Delete News Feed | Admin | The Admin have a right to delete News. | The Admin must be Logged in before using this functionality. | Critical | 2 | 5
USER_STORY_9 | Update News Feed | Admin | The Admin have a right to update news if any changes happenes in current event | The Admin must be Logged in before using this functionality. | Critical | 2 | 5
USER_STORY_10 | User Login | User | The user can able to login to the website after entering username and password | User Name and password must match in the database table User | Critical | 1 | 5
USER_STORY_11 | Search Flight | User | User can Search Flight after filling the form | User must be logged in to use this functionality | Critical | 1 | 5
USER_STORY_12 | Update User | User | User can update their credentials | The User must be Logged in before using this functionality. | Critical | 1 | 5
USER_STORY_13 | Register User | User | User can register himself after providing the required credentials. | User ID, age, phone no. must be integer and answer,email,gender name , password and Secret question can be of String. | Critical | 1 | 5
USER_STORY_14 | Get Flight Seats | User | User can able to see the total seats available in a flight | User must be logged in to use this functionality | Critical | 2 | 5
USER_STORY_15 | Show Booking Status | User | User can able to see his booking status of a flight he has booked | User must book a ticket and User must be logged in to use this functionality. | Critical | 2 | 5
USER_STORY_16 | Book Flight | User | User can able to book flight for a perticular source and destination | User must be logged in to use this functionality | Critical | 2 | 5
USER_STORY_17 | Cancel Flight | User | User can able to Cancel the flight from his booking status | User must book a ticket and User must be logged in to use this functionality. | Critical | 2 | 5
USER_STORY_18 | Bank Details | User | User can able to pay for a ticket providing the bank details | User must be logged in to use this functionality | Critical | 2 | 5