## Cover Page
<Spark Airways>
Sprint Backlog
|  | Prepared By / Last Updated By | Reviewed By | Approved By
Name
Role
Signature
Date
:

## Instructions
Sprint Backlog - Instructions
C3: Protected Controlled Copy
Sprint Backlog
The Sprint Backlog is the set of Product Backlog items selected for the Sprint, plus a plan for delivering the product Increment and realizing the Sprint Goal. The Sprint Backlog is a forecast by the Development Team about what functionality will be in the next Increment and the work needed to deliver that functionality into a “Done” Increment.The Sprint Backlog is the output of the sprint planning meeting. It is essentially the list of tasks that the Scrum team needs to complete during the sprint in order to turn a selected set of product backlog items into a deliverable increment of functionality.
Sample
The sheet sample is an example sheet on how to fill the sprint backlog. Trainees can refer it to fill the details in the sheets Sprint 1/2/3.
Sprint 1/2/3
| User Story & Task Id | List the User Story id taken from product backlog that are selected to be completed in the particular sprint & List the number of tasks the User story is split into..
| Task | Name the tasks the user story is split into.
| Story Points | Enter the story points that was given for the user story during Sprint planning
| Assigned to | Name the person responsible for the particular task
| Status | Status of the Task - In progress/Completed
| Original Estimate | Original estimate of the task
| Day 1/2/3/4/5 | Task done in Day1/2/3/4/5 - Sprint review and retrospective to be held on Day 5
| Total | Summation of the estimation per day. To be filled with the total of the estimations filled.
| Charts | Chart is self driven as per the task burned

## Sprint - 1
Sprint Backlog Spark Airways
Project ID: INTADM21AJ008 C3: Protected Controlled Copy
BACKLOG TASK & ID | USER STORY & TASK | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5
User Story #1 | Admin Login | 5 | Abhay Raj Singh, Anshuman Sahu, Bhavesh Saini | SUCCESS |  | 1 | 1 | 1 | 1 | 1
User Story #2 | Add Flight Schedule | 5 | Abhay Raj Singh, Anshuman Sahu, Bhavesh Saini | SUCCESS |  | 1 | 1 | 1 | 1 | 1
User Story #3 | Show All Flight Schedules | 5 | Abhay Raj Singh, Anshuman Sahu, Bhavesh Saini | SUCCESS |  | 1 | 1 | 1 | 1 | 1
User Story #4 | Delete Flight Schedule | 5 | Abhay Raj Singh, Anshuman Sahu, Bhavesh Saini | SUCCESS |  | 1 | 1 | 1 | 1 | 1
User Story #10 | User Login | 5 | Nikhil Kharwal, Siddharth Sharma | SUCCESS |  | 1 | 1 | 1 | 1 | 1
User Story #11 | Search Flight | 5 | Nikhil Kharwal, Siddharth Sharma | SUCCESS |  | 1 | 1 | 1 | 1 | 1
User Story #12 | Update User | 5 | Nikhil Kharwal, Siddharth Sharma | SUCCESS |  | 1 | 1 | 1 | 1 | 1
User Story #13 | Register User | 5 | Nikhil Kharwal, Siddharth Sharma | SUCCESS |  | 1 | 1 | 1 | 1 | 1
TOTAL |  |  |  |  | 0 | 8 | 8 | 8 | 8 | 8

## Sprint - 2
Sprint Backlog Spark Airways
Project ID: INTADM21AJ008 C3: Protected Controlled Copy
BACKLOG TASK & ID | USER STORY & TASK | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5
User Story #5 | Update Flight Schedule | 5 | Abhay Raj Singh, Anshuman Sahu, Bhavesh Saini | SUCCESS |  | 1 | 1 | 1 | 1 | 1
User Story #6 | Add News Feed | 5 | Abhay Raj Singh, Anshuman Sahu, Bhavesh Saini | SUCCESS |  | 1 | 1 | 1 | 1 | 1
User Story #7 | Show All News Feed | 5 | Abhay Raj Singh, Anshuman Sahu, Bhavesh Saini | SUCCESS |  | 1 | 1 | 1 | 1 | 1
User Story #8 | Delete News Feed | 5 | Abhay Raj Singh, Anshuman Sahu, Bhavesh Saini | SUCCESS |  | 1 | 1 | 1 | 1 | 1
User Story #9 | Update News Feed | 5 | Abhay Raj Singh, Anshuman Sahu, Bhavesh Saini | SUCCESS |  | 1 | 1 | 1 | 1 | 1
User Story #14 | Get Flight Seats | 5 | Nikhil Kharwal, Siddharth Sharma | SUCCESS |  | 1 | 1 | 1 | 1 | 1
User Story #15 | Show Booking Status | 5 | Nikhil Kharwal, Siddharth Sharma | SUCCESS |  | 1 | 1 | 1 | 1 | 1
User Story #16 | Book Flight | 5 | Nikhil Kharwal, Siddharth Sharma | SUCCESS |  | 1 | 1 | 1 | 1 | 1
User Story #17 | Cancel Flight | 5 | Nikhil Kharwal, Siddharth Sharma | SUCCESS |  | 1 | 1 | 1 | 1 | 1
User Story #18 | Bank Details | 5 | Nikhil Kharwal, Siddharth Sharma | SUCCESS |  | 1 | 1 | 1 | 1 | 1
TOTAL |  |  |  |  | 0 | 10 | 10 | 10 | 10 | 10